# Snohomish County Marine Resources Committee Work Plan 2024

| Project |  |  | January | February | March | April | May | June | July | August | September | October | November | December |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Monthly Meeting |  |  | MRC elections. Presentation by NWSC on NWSC Strategic Plan | Hold for hosting retreat meeting for strategic plan | Presentation on listing of sunflower sea star |  | 2023-2025 MRC grant planning |  | Hold for hosting retreat meeting for strategic plan | No meeting - picnic |  | WSU Beach Watchers Presentation | Hold for Annual work planning session |  |
| MRC Administration (Grant Task 1) |  | Members | MRC Members Report Volunteer hours for October, November, Dec. by Jan 1. | MRC Mentorship Program for new members | MRC review and finalize Annual Report | MRC Members Report Volunteer hours for January, February, March by April 1. Annual Report to Council. | MRC Members conduct outreach for new members. Recruit for intern. | MRC Members conduct outreach for new members. | MRC Members Report Volunteer hours for April, May, June by July 1. | Host MRC Picnic. MRC intern hosting and opportunities with members. | MRC Members report volunteer hours for July, August September by Sept. 20. | Plan Annual Retreat and work planning session. Recruit new MRC Members. | Annual Retreat and work planning session. Interviews for new MRC Members. | Website update review and changes. |
|  |  | Staff | Progress Report Due. Annual Work Plan Due. | Start Annual Report with Communications staff. | Schedule Annual Report to County Council. Begin developing plan for next MRC grant. | Progress Report + Annual Report due. Annual Report to Council. Cont. planning for next MRC grant. | Finalize next year’s grant project. Draft grant proposal. Recruit and interview for intern position. | Finalize grant proposal. MRC presentation for next year’s grant. Host MRC intern. | Progress Report Due. Host MRC intern. | Complete paperwork for next grant with NWSC/SnoCo. Host MRC intern. | Progress Report Due. Start recruitment for new members as needed. | Plan Annual Retreat and work planning session. Start new grant. Recruitment as needed | Facilitate Annual Retreat and work planning session. Interviews for new members as needed. | Complete website updates from MRC Review. Complete new member or reappointment paperwork. |
| MRC Strategic Plan (2025-2030) - Franchesca Perez (Co- Lead) - Natasha Coumou (Co- Lead) - Richard Strickland - Phill Salditt |  |  | MRC preps for and conducts interviews with consultant. | MRC conducts interviews with consultant. First retreat meeting | Review results from interviews, first retreat. Survey for stakeholders to give input. | Continue getting stakeholder input | Review summary report from stakeholder input. | Prep for summer retreat style meeting, review outline of Strategic Plan | Second retreat style meeting. Review Draft Strategic Plan | MRC to provide feedback on draft strategic plan | Finalize Strategic Plan | Adopt Strategic Plan | Begin Phase 2 of strategic plan/communication planning. | Begin Phase 2 of strategic plan/communication planning. |
| MRC Outreach - Julie S. (Lead) - Brie T. (Lead) - Tim Ellis (lead) - David Bain - Andrew Gobin - Allan Hicks - Phill Salditt |  | In-person events (Beach cleanups, Beach Walks, Tabling) | Plan beach cleanup dates for the year with WSU Beach Watchers, including ETAP event date. Plan Starlight beach walk event (February 6, 2024) | Starlight Beach Walk (February 6, 2024) | Plan and host Q1 beach cleanup with WSU BW, ETAP Event. Earth Day event coordination and planning work. | Partner with BW on Earth Day beach cleanup event for Q2. Suggested to do event on Tulalip Tribes Mission beach. | Subcommittee meeting to discuss Plastic Free Salish Sea opportunities for in-person outreach. |  |  | Plan Q3 beach cleanup with WSU Beach Watchers. Suggested to do a cleanup at Jetty Island | International Coastal Cleanup Day. Ideas for celebration? | Orca Day is mid-October. Opportunity to have a beach cleanup or other event for this. | Start planning for 2025 Beach Walk event, decide on date. | Subcommittee meeting to discuss opportunities for 2025. Ensure that MRC has materials for 2025 Beach Walk event. |
|  |  | Crabber Education |  |  | Have Subcommittee meeting to plan outreach. Discuss coordination with WSU and City of Edmonds. | Continue planning work. Order materials for season. Create social media ads | Continue planning work. Gather materials for season. Create social media ads | Do outreach focusing on week before opening and week after opening. | Crabber Ed throughout July and August until close of summer season (generally Labor Day weekend). | Subcommittee meeting to go over numbers, lessons learned, plans for next season. |  |  |  |  |
| Oil Spill Preparedness and Prevention - Julie S. (Lead) - David Bain - Franchesca P. |  |  | Subcommittee meeting to discuss plans for 2024. Promote partnership with other MRCs to join inter-MRC oil spill subcommittee. Attend Q1 LEPC meeting. | Plan for oil spill outreach. |  | Attend Q2 LEPC meeting. | Discuss outreach at Opening Recreation Boat Bay. |  | Attend Q3 LEPC meeting. |  |  | Attend Q4 LEPC meeting. Attend HAZWOP wildlife training. | Attend Pacific States/BC annual Oil Spill Task Force meeting. |  |
| Project |  |  | January | February | March | April | May | June | July | August | September | October | November | December |
| Forage Fish Monitoring - Phil Salditt (Lead) - Julie Schlenger - Sara Maxwell - Brie Townsend - Allan Hicks |  |  | Monitor sites at Picnic Point and Meadowdale. Subcommittee meeting to discuss options for monitoring at Howarth Park. | Monitor sites at Picnic Point and Meadowdale. | Monitor sites at Picnic Point and Meadowdale. | Monitor sites at Picnic Point and Meadowdale. | Monitor sites at Picnic Point and Meadowdale. | Monitor sites at Picnic Point and Meadowdale. | Monitor sites at Picnic Point and Meadowdale. Attend forage fish training as needed, if being hosted by WDFW and NWSC | Monitor sites at Picnic Point and Meadowdale. | Monitor sites at Picnic Point and Meadowdale. | Monitor sites at Picnic Point and Meadowdale. | Monitor sites at Picnic Point and Meadowdale. Bring sediment samples to Snohomish County Materials Lab. | Monitor sites at Picnic Point and Meadowdale. |
| Marine Water Quality Monitoring - Tim Ellis (Lead) - Natasha Coumou - Brie Townsend - Andrew Gobin - David Bain - Julie Schlenger - Franchesca Perez |  |  |  | Remove mussel cages from Snohomish County sites. | Schedule meeting to discuss ORCA work and opportunities for year. |  |  | Attend ORCA Possession Sound Showcase. |  |  |  | Review ORCA draft documentation for 5-year monitoring review. | Presentation by ORCA on 5-year monitoring review of Possession Sound. |  |
| Marine Vegetation Monitoring - Brie Townsend (Lead) - Julie Schlenger (Lead) - Tim Ellis | Kelp Monitoring |  |  |  |  |  | Schedule safety training for kelp monitoring as needed. | Check all gear to prepare for kelp monitoring. | Complete float plan and paperwork prior to kelp monitoring. Monitor kelp beds. | Complete float plan and paperwork prior to kelp monitoring. Monitor kelp beds. | Get kelp data to NWSI for processing. Initial findings from Complete second survey of Hat Island kelp beds. | Finalize kelp data processing. Ensure kelp data is in Sound IQ. | Share kelp data results with partners. |  |
|  | MRC Grant for Marine Vegetation |  | Provide overview of knowledge to consultant | Identify Edmonds community groups to focus on | Begin drafting community event plan | Begin drafting education materials | Continue event planning and education materials | Continue event planning and education materials | Create SOW for 2025 marine veg grant continuation | Review draft education materials and provide feedback | Finalize education materials and event plan | Host event. Gather feedback from participants. | Event Debrief and lessons learned | Prepare for 2025 grant work. |
| Nearshore Restoration - Tim Ellis (Lead) - Brie Townsend - David Bain - Julie Schlenger - Natasha Coumou |  |  | Schedule and Plan Subcommittee meeting to discuss opportunity for nearshore white paper on climate change. | Subcommittee meeting to discuss opportunity for nearshore white paper on climate change. | Follow up on climate change white paper. |  |  |  | Coordinate with Beach watchers on Meadowdale Tours | Coordinate with Beach watchers on Meadowdale Tours | Annual Check in on Snohomish Estuary Piling Project | Update Pilings webpage. |  |  |
| Derelict Vessel Removal - Natasha Coumou - Allan Hicks - Andrew Gobin - Phil Salditt |  |  |  | Plan for recon with SWM boat. Update list of vessels. | Boat recon. Update boat spreadsheet. | Convene meeting with DNR and partners about boats to prioritize for removal. | Start compiling docs for removal. | Field work to prep for postings. Finalize docs for bidding and posting. | Inform partners of final boat removal plan. Get bids on vessels. | Post Vessels. Finalize contract for removal. | Finalize contract for removal. boat removal after Labor Day (preferred by Port) | Close out contract on boat removal. | DNR reimbursements. Outreach on boat removal + MyCoast | DNR reimbursements. |
| Port Susan - Sara Maxwell - Natasha Coumou - Franchesca Perez |  |  | Reach out to Parks about story map language on Kayak pt. signs | Subcommittee meeting to discuss next steps. Draft Kayak Point Park Signage | Follow up on septic ideas from SWC meeting. | Option to address septic follow up in MRC’s annual report to council | Review Kayak Point Park Signage | Finalize kayak point park signage | Work with MRC intern on shoreline armoring survey | Work with MRC intern on shoreline armoring survey |  |  |  |  |

Key:

Grey: Admin

Red: Grant required work

Purple: Education and Outreach projects

Blue: Monitoring/conservation project

Green: Restoration projects

# MRC Strategic Plan (Grant Task 2) – 2024 MRC Work Plan

|  | January | February | March | April | May | June | July | August | September | October | November | December |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

| MRC Strategic Plan (2025-2030) - Franchesca Perez (Co- Lead) - Natasha Coumou (Co- Lead) - Richard Strickland - Phill Salditt | MRC preps for and conducts interviews with consultant. | MRC conducts interviews with consultant. First retreat meeting | Review results from interviews, first retreat. Survey for stakeholders to give input. | Continue getting stakeholder input | Review summary report from stakeholder input. | Prep for summer retreat style meeting, review outline of Strategic Plan | Second retreat style meeting. Review Draft Strategic Plan | MRC to provide feedback on draft strategic plan | Finalize Strategic Plan | Adopt Strategic Plan | Begin Phase 2 of strategic plan/communication planning. | Begin Phase 2 of strategic plan/communication planning. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

## Goal of Subcommittee/Key Outcomes:

- Get feedback from MRC and stakeholders on MRC priority and goals

- Create Strategic Plan for 2025-2030

- Publish Strategic Plan on website

- Come to consensus on strategic plan and vote to adopt plan by end of 2024.

## Key MRC Member Responsibilities

- Contribute to the development of the strategic plan

- Participate in interview

- Attend retreat style meetings

- Review drafts

## Key MRC Staff Responsibilities

- Contribute to the development of the strategic plan

- Participate in interview

- Attend retreat style meetings

- Review drafts

- Manage consultant contract

# MRC Outreach In person outreach events – 2024 MRC Work Plan

|  | January | February | March | April | May | June | July | August | September | October | November | December |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

| MRC Outreach - Julie Schlenger (Lead) - Brie Townsend (Lead) - Tim Ellis (Beach Cleanup lead) - David Bain - Andrew Gobin - Allan Hicks - Phill Salditt | In-person events (Beach cleanups, Beach Walks, Tabling) | Plan beach cleanup dates for the year with WSU Beach Watchers, including ETAP event date. Plan Starlight beach walk event (February 6, 2024) | Starlight Beach Walk (February 6, 2024) | Plan and host Q1 beach cleanup with WSU BW, ETAP Event. Earth Day event coordination and planning work. | Partner with BW on Earth Day beach cleanup event for Q2. Suggested to do event on Tulalip Tribes Mission beach. | Subcommittee meeting to discuss Plastic Free Salish Sea opportunities for in-person outreach. |  |  | Plan Q3 beach cleanup with WSU Beach Watchers. Suggested to do a cleanup at Jetty Island | International Coastal Cleanup Day. Ideas for celebration? | Orca Day is mid-October. Opportunity to have a beach cleanup or other event for this. | Start planning for 2025 Beach Walk event, decide on date. | Subcommittee meeting to discuss opportunities for 2025. Ensure that MRC has materials for 2025 Beach Walk event. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

## Goal of Subcommittee/Key Outcomes:

- Host at least 5 in-person events per year for the public

- Complete an ETAP beach cleanup

## Key MRC Member Responsibilities

- Coordinate and attend subcommittee meetings

- Assist with planning beach cleanup events

- Attend beach cleanup events

- Assist with planning for the Starlight Beach Walk

- Attend Starlight Beach Walk

- Develop and discuss opportunities and for Plastic Free Salish Sea activities

## Key MRC Staff Responsibilities

- Coordinate beach cleanup events with WSU Beach Watchers

- Coordinate the Starlight Beach Walk with WSU Beach Watchers

- Consider opportunities for an Orca Day event in mid-October

- Develop and discuss opportunities and for Plastic Free Salish Sea activities

# Recreational Crabber Education – 2024 MRC Work Plan

|  | January | February | March | April | May | June | July | August | September | October | November | December |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

| MRC Outreach - Julie Schlenger (Lead) - Brie Townsend (Lead) - Tim Ellis (Beach Cleanup lead) - David Bain - Andrew Gobin - Allan Hicks - Phill Salditt | Crabber Education |  |  | Have Subcommittee meeting to plan outreach. Discuss coordination with WSU and City of Edmonds. | Continue planning work. Order materials for season. Create social media ads | Continue planning work. Gather materials for season. Create social media ads | Do outreach focusing on week before opening and week after opening. | Crabber Ed throughout July and August until close of summer season (generally Labor Day weekend). | Subcommittee meeting to go over numbers, lessons learned, plans for next season. |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

## Goal of Subcommittee/Key Outcomes:

- Hold 4 days of in-person crabber outreach at Everett 10th street boat launch

- Reach at least 500 people through in-person outreach

## Key MRC Member Responsibilities

- Coordinate and attend subcommittee meetings

- Work with MRC staff, WSU Beach Watchers and other partners to develop an outreach plan for 2024

- Assist with pre-outreach coordination, as needed

- Work with WSU Beach Watchers to create a How-To guide and training resources for outreach at Boat Launches

- Conduct crabber education outreach (in-person, if conditions allow). Lead volunteers from WSU Beach Watchers on Crabber Education.

- Debrief with MRC staff and partners about the season of outreach, and provide lessons learned and ideas for outreach in following year

## Key MRC Staff Responsibilities

- Work with MRC members and partners to develop an outreach plan for 2023

- Plan for outreach activities, including coordination with partners and gathering materials

- Create social media ads with County Communications staff

- Coordinate and conduct crabber education outreach (in-person, if conditions allow)

- Coordinate debrief meeting with MRC members and partners to discuss the season of outreach, including lessons learned and ideas for outreach in 2024

# Oil Spill Preparedness – 2022 MRC Work Plan

|  | January | February | March | April | May | June | July | August | September | October | November | December |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

| Oil Spill Preparedness and Prevention - Julie Schlenger (Lead) - David Bain - Franchesca Perez |  | Subcommittee meeting to discuss plans for 2024. Promote partnership with other MRCs to join inter-MRC oil spill subcommittee. Attend Q1 LEPC meeting. | Plan for oil spill outreach. |  | Attend Q2 LEPC meeting. | Discuss outreach at Opening Recreation Boat Bay. |  | Attend Q3 LEPC meeting. |  |  | Attend Q4 LEPC meeting. Attend HAZWOP wildlife training. | Attend Pacific States/BC annual Oil Spill Task Force meeting. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

## Goal of Subcommittee/Key Outcomes:

- Connect with oil spill preparedness and response efforts within the Puget Sound

- Have a general knowledge and understanding the steps taken by organizations in the event of an oil spill in the marine environment

## Key MRC Member Responsibilities

- Review local Geographic Response Plans (GRPs)

- Coordinate and attend subcommittee meetings

- Brainstorm and discuss opportunities for oil wildlife response

- Seek out and attend opportunities for HAZWOPER and other oil wildlife response trainings

- Coordinate a guest speaker to present to the MRC on chronic oil spills/leaks from land

- Coordinate and attend subcommittee meetings

## Key MRC Staff Responsibilities

- Review local Geographic Response Plans (GRPs)

# Forage Fish Monitoring – 2024 MRC Work Plan

|  | January | February | March | April | May | June | July | August | September | October | November | December |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

| Forage Fish Monitoring - Julie Schlenger - Sara Maxwell - Brie Townsend - David Bain - Allan Hicks | Monitor sites at Picnic Point and Meadowdale. Subcommittee meeting to discuss options for monitoring at Howarth Park. | Monitor sites at Picnic Point and Meadowdale. | Monitor sites at Picnic Point and Meadowdale. | Monitor sites at Picnic Point and Meadowdale. | Monitor sites at Picnic Point and Meadowdale. | Monitor sites at Picnic Point and Meadowdale. | Monitor sites at Picnic Point and Meadowdale. Attend forage fish training as needed, if being hosted by WDFW and NWSC | Monitor sites at Picnic Point and Meadowdale. | Monitor sites at Picnic Point and Meadowdale. | Monitor sites at Picnic Point and Meadowdale. | Monitor sites at Picnic Point and Meadowdale. Bring sediment samples to Snohomish County Materials Lab. | Monitor sites at Picnic Point and Meadowdale. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

## Goal of Subcommittee/Key Outcomes:

- Take monthly samples at Picnic Point and Meadowdale as part of the Meadowdale monitoring work

- Analyze data from the year to share with MRC and on website.

## Key MRC Member Responsibilities

- Conduct monthly forage fish monitoring field work

- Attend trainings, as available

- Assist with compiling data from the year and presenting to the MRC

- Assist with delivery of monitoring samples to WDFW

## Key MRC Staff Responsibilities

- Coordinate monthly forage fish monitoring field work

- Compile monitoring data and present to the MRC

- Coordinate delivery of monitoring samples to WDFW

- Maintain adequate supply levels to complete monthly monitoring

- Deliver sediment samples to Snohomish County geology lab

# Marine Water Quality Monitoring – 2024 MRC Work Plan

|  | January | February | March | April | May | June | July | August | September | October | November | December |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

| Marine Water Quality Monitoring - Tim Ellis (Lead) - Natasha Coumou - Brie Townsend - Andrew Gobin - David Bain - Julie Schlenger - Franchesca Perez |  | Remove mussel cages from Snohomish County sites. | Schedule meeting to discuss ORCA work and opportunities for year. |  |  | Attend ORCA Possession Sound Showcase. |  |  |  | Review ORCA draft documentation for 5-year monitoring review. | Presentation by ORCA on 5-year monitoring review of Possession Sound. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

## Goal of Subcommittee/Key Outcomes:

- Complete all Snohomish County WDFW mussel monitoring site retrieval

- Engage with ORCA to continue to work towards creating a State of Possession Sound report.

## Key MRC Member Responsibilities

- Retrieve mussel cages from monitoring locations

- Work with MRC staff to coordinate return of mussels & equipment to WDFW

- Attend subcommittee meetings

- Review and become familiar ORCA’s marine monitoring in Possession Sound

- Brainstorm ideas for the MRC to leverage partners for marine water quality monitoring in Snohomish County

- Reach out to local jurisdictions and partners about current strategies for improving water quality

- Research the Puget Sound Starts Here campaign and research regional programs on stormwater. Bring information on regional programs to the MRC

## Key MRC Staff Responsibilities

- Work with MRC staff to coordinate with WDFW

- Check in with WDFW staff about results of Mussel Watch monitoring

- Manage contract with ORCA

- Coordinate and attend subcommittee meetings

# Marine Vegetation Monitoring – 2024 MRC Work Plan

|  | January | February | March | April | May | June | July | August | September | October | November | December |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

| Marine Vegetation Monitoring - Brie Townsend (Lead) - Julie Schlenger (Lead) - Tim Ellis | Kelp Monitoring |  |  |  |  | Schedule safety training for kelp monitoring as needed. | Check all gear to prepare for kelp monitoring. | Complete float plan and paperwork prior to kelp monitoring. Monitor kelp beds. | Complete float plan and paperwork prior to kelp monitoring. Monitor kelp beds. | Get kelp data to NWSI for processing. Initial findings from Complete second survey of Hat Island kelp beds. | Finalize kelp data processing. Ensure kelp data is in Sound IQ. | Share kelp data results with partners. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | MRC Grant for Marine Vegetation | Provide overview of knowledge to consultant | Identify Edmonds community groups to focus on | Begin drafting community event plan | Begin drafting education materials | Continue event planning and education materials | Continue event planning and education materials | Create SOW for 2025 marine veg grant continuation | Review draft education materials and provide feedback | Finalize education materials and event plan | Host event. Gather feedback from participants. | Event Debrief and lessons learned | Prepare for 2025 grant work. |

## Goal of Subcommittee/Key Outcomes:

- Create education materials for Edmonds kelp and eelgrass

- Reach at least 200 people to discuss declines in kelp in Edmonds

- Hold community event to discuss status of kelp and eelgrass in Edmonds area.

## Key MRC Member Responsibilities

- Work with consultant on 2024 project in Edmonds

- Help plan 2024 educational event

- Help guide and provide feedback on education materials

- Share marine vegetation data and kelp monitoring results with partners

- Attend Subcommittee Meetings

- Recruit new kelp monitoring members, as needed

- Attend safety training, as needed

- Complete Kelp Monitoring field work in July and August

- Analyze data and make presentation to the MRC about data and trends

- Attend regional workshops on kelp and eelgrass

## Key MRC Staff Responsibilities

- Work with consultant on 2024 project in Edmonds

- Help plan 2024 educational event

- Help guide and provide feedback on education materials

- Share marine vegetation data and kelp monitoring results with partners

- Coordinate and attend Subcommittee Meetings

- Coordinate marine vegetation monitoring efforts with DNR

- Coordinate presentation to MRC by DNR

- Coordinate safety training for new monitoring team members, as needed

- Coordinate Kelp Monitoring field work in July and August

- Coordinate kelp data processing with NWSI

# Nearshore Restoration – 2024 MRC Work Plan

|  | January | February | March | April | May | June | July | August | September | October | November | December |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

| Nearshore Restoration - Tim Ellis (Lead) - Brie Townsend - David Bain - Julie Schlenger - Natasha Coumou | Schedule and Plan Subcommittee meeting to discuss opportunity for nearshore white paper on climate change. | Subcommittee meeting to discuss opportunity for nearshore white paper on climate change. | Follow up on climate change white paper. |  |  |  | Coordinate with Beach watchers on Meadowdale Tours | Coordinate with Beach watchers on Meadowdale Tours | Annual Check in on Snohomish Estuary Piling Project | Update Pilings webpage. |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

## Goal of Subcommittee/Key Outcomes:

- Decide on way to engage in climate change

- Coordinate 2 Meadowdale tours with Beach Watchers

- Update Pilings webpage

## Key MRC Member Responsibilities

- Coordinate and attend subcommittee meetings

- Work with MRC staff to develop and finalize climate change materials

- Develop and discuss opportunities and ideas for continued MRC involvement and new nearshore projects

## Key MRC Staff Responsibilities

- Work with MRC members on climate change projects

- Coordinate post-restoration monitoring activities at Meadowdale

- Develop and discuss opportunities and ideas for continued MRC involvement and new nearshore projects

# Derelict Vessels – 2022 MRC Work Plan

|  | January | February | March | April | May | June | July | August | September | October | November | December |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

| Derelict Vessel Removal - Natasha Coumou - Allan Hicks - Andrew Gobin |  | Plan for recon with SWM boat. Update list of vessels. | Boat recon. Update boat spreadsheet. | Convene meeting with DNR and partners about boats to prioritize for removal. | Start compiling docs for removal. | Field work to prep for postings. Finalize docs for bidding and posting. | Inform partners of final boat removal plan. Get bids on vessels. | Post Vessels. Finalize contract for removal. | Finalize contract for removal. boat removal after Labor Day (preferred by Port) | Close out contract on boat removal. | DNR reimbursements. Outreach on boat removal + MyCoast | DNR reimbursements. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

## Goal of Subcommittee/Key Outcomes:

- Prioritize derelict vessels for removal

- Work with DNR to conduct removal of identified vessels

## Key MRC Member Responsibilities

- Review and comment on proposed list of boats for removal

- Add vessels to list as they become known

- Make MyCoast reports of vessels in Snohomish County

## Key MRC Staff Responsibilities

- Coordinate boat reconnaissance field work with SWM boat

- Update inventory of derelict vessels

- Draft proposed list of vessels for removal

- Convene meeting with DNR and partners to discuss boats to prioritize for removal in 2022

- Post vessels

- Procure contractor to remove vessels

- Coordinate removal of vessels

- Process reimbursements for removal costs with DNR

- Coordinate outreach on boat removal and MyCoast

# Port Susan – 2024 MRC Work Plan

|  | January | February | March | April | May | June | July | August | September | October | November | December |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

| Port Susan - Sara Maxwell (Lead) - Natasha Coumou - Allan Hicks - Francesca Perez | Reach out to Parks about story map language on Kayak pt. Signs; Reach out Island MRC re septic and shoreline armoring work | Subcommittee meeting to discuss next steps. Draft Kayak Point Park Signage | Follow up on septic ideas from SWC meeting. | Option to address septic follow up in MRC’s annual report to council | Review Kayak Point Park Signage | Finalize kayak point park signage | Work with MRC intern on shoreline armoring survey | Work with MRC intern on shoreline armoring survey |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

## Goal of Subcommittee/Key Outcomes:

- Create next steps for Port Susan Subcommittee

- Follow up on next steps

- Coordinate with Island County MRC about relevant overlapping work

- Review Kayak Point signage

- Work with intern on shoreline armoring project

## Key MRC Member Responsibilities

- Hold subcommittee meetings

- Decide on path forward for subcommittee

- Follow up on actions planned

## Key MRC Staff Responsibilities

- Coordinate and attend subcommittee meetings

- Get SWM management feedback as needed